## Sheet1
Task ID | Start Date | End Date | Task Name | Duration (Days) | Position | Start date | End date | Milestone/Activity | Duration (Days)
1 | 2025-09-22 | 2026-03-01 | Literature review | 160 | 1 | 2025-09-22 | 2026-03-01 | Literature review | 160
2 | 2025-10-06 | 2025-10-16 | Double inverted pendulum theory | 10 | 2 | 2025-10-06 | 2025-10-21 | Double inverted pendulum theory | 15
3 | 2025-10-16 | 2025-10-30 | Establish complete robot model | 14 | 3 | 2025-10-21 | 2025-12-01 | Establish complete robot model for parameters | 41
4 | 2025-10-30 | 2025-11-03 | Analyse model on MATLAB | 4 | 4 | 2025-12-01 | 2025-12-05 | Analyse model on MATLAB | 4
5 | 2025-11-03 | 2025-12-03 | CAD design sketch and design | 30 | 5 | 2025-11-25 | 2025-12-29 | CAD design sketch and design | 34
6 | 2025-12-03 | 2025-12-20 | Simulating CAD design on ROS2 | 17 | 6 | 2025-12-29 | 2026-01-20 | Simulating CAD design on ROS2 | 22
7 | 2025-12-20 | 2026-01-03 | Review simulation performance | 14 | 7 | 2026-01-20 | 2026-01-24 | Review simulation performance | 4
8 | 2026-01-03 | 2026-01-20 | Prototype design | 17 | 8 | 2026-01-03 | 2026-01-20 | Prototype design | 17
9 | 2026-01-20 | 2026-02-04 | Prototype manufacture | 15 | 9 | 2026-01-20 | 2026-02-20 | Prototype manufacture | 31
10 | 2026-02-04 | 2026-03-10 | Fixes and adjustments | 34 | 10 | 2026-02-20 | 2026-03-10 | Fixes and adjustments | 20
11 | 2026-03-10 | 2026-03-15 | Bench inspection | 5 | 11 | 2026-03-10 | 2026-03-15 | Bench Inspection | 5
12 | 2026-03-15 | 2026-06-10 | Report writing | 87 | 12 | 2026-03-15 | 2026-06-10 | Report writing | 87